## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 4 |  |  |  |  | Bryanna Martinez | bmunoz20@uic.edu
Week Of: 4/17/19 |  |  |  |  | Angel Ramirez | jramir93@uic.edu
[5 empty] | Jakobi Oommen | joomme2@uic.edu
[5 empty] | Kaylyn Egyarto | kegyar2@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
making the images for the hangman | hm1 | jakobi |  | draw out images/ find images | complete by the beginning of next week and meet on Wednesday at 1pm | no WiFi connection. Hard to decide what pictures to use
text data for words or images/ and code for getting the word/ phrase | hm1 | jakobi |  | make a text file with both phrases and words. Write code to parse out file |  | determining how ling we want the file to be
text field for guessing the entire word or individual ltter with 1 button. Enter word or letter | hm2 | Kaylyn |  | create the textfield and button |  | the button may not do anything at the moment. Understanding the setOnAction code
code for checking letter or phrase/word | hm2 | Kaylyn |  | think how to go about writing the code |  | May not read correctly
client/ server classes + their GUI set up | hm3 | Bryanna |  | write the client and server class and set up the client and server GUI mains |  | no issues
client handler class (determining what to do with what the client sent to the server) | hm4 | Angel |  | Figure out how to send the client info to the server and have the server send things back |  | figuring how to send stuff to the correct client