## April 1
|  |  | Weekly Sprint Sheet |  | Team Members | Email
Project: Project 5 |  |  |  |  | Bryanna Martinez | bmunoz20@uic.edu
Week Of: 4/24/19 |  |  |  |  | Angel Ramirez | jramir93@uic.edu
[5 empty] | Jakobi Oommen | joomme2@uic.edu
[5 empty] | Kaylyn Egyarto | kegyar2@uic.edu
Action Item | Item ID | Team Member | Last Week | This Week | Next Week | Issues
[6 empty] | LAST WEEK | This Week:
making the images for the hangman | hm1 | jakobi | draw out images/ find images | comment each of our codes and merging them together to be one code. | complete by the beginning of next week and meet on Wednesday at 1pm | no WiFi connection. Hard to decide what pictures to use | This Week: there might be compatiblility issues..
text data for words or images/ and code for getting the word/ phrase | hm1 | jakobi | make a text file with both phrases and words. Write code to parse out file | comment earch of our codes and merging them together to be one code. |  | determining how ling we want the file to be | This Week: there might be compatiblility issues..
text field for guessing the entire word or individual ltter with 1 button. Enter word or letter | hm2 | Kaylyn | create the textfield and button | comment each of our codes and merging them together to be one code. |  | the button may not do anything at the moment. Understanding the setOnAction code | This Week: there might be compatiblility issues..
code for checking letter or phrase/word | hm2 | Kaylyn | think how to go about writing the code | comment each of our codes and merging them together to be one code. |  | May not read correctly | This Week: there might be compatiblility issues..
client/ server classes + their GUI set up | hm3 | Bryanna | write the client and server class and set up the client and server GUI mains | comment each of our codes and merging them together to be one code. |  | no issues | This Week: there might be compatiblility issues..
client handler class (determining what to do with what the client sent to the server) | hm4 | Angel | Figure out how to send the client info to the server and have the server send things back | comment earch of our codes and merging them together to be one code. |  | figuring how to send stuff to the correct client | This Week: there might be compatiblility issues..